## DISCUSSION DRAFT

## Proposed Time Line – version 2.0

The following table sets out what is believed to be a reasonable guideline as to the timing of the various events that need to take place in order to take a vote of the whole Assembly on one or more issues by the end of May. What follows are not strict "rules" but rather a rough sketch of the rates at which Members could expect things to happen. That is, the "duration" is not carved in stone, but rather what one should normally expect to see, all other things being equal. Since, in order to complete any Vote of the whole Assembly within a 28 day time period, more than one process must take place at once, hence this table provides deadlines for each of the concurrent processes.

Action	Duration	Start  	 End

General Discussion

And investigation of issues

(in progress)	7 days	Thurs May 2nd        	Thurs May 9th

Poll (underway)	3 days	Fri May 3rd        	Sun May 5th

Recognition of Motion(s)	24 hours		Fri May 10th

Debate on Motion(s)	7 days	Fri May 10th 	Fri May 17th

Poll(s) on amendments,

And/ or alternative motions 	3 days	optional at any time during Debate

Recognition of Voting

Procedure	1 day		Sat May 18th

Secretariat prepares Ballot (s)	1 day	Sun May 19th

Vote of the whole Assembly	7 days    	Mon May 20th        	Mon May 27th

Final Report

(Vote results and supporting

documentation)                 	2 days                       	Tues May 28th	Wed May 29th

Submit Final Report to ICANN Board

And other interested parties.		Thurs May 30th

Prepared with reference to Best Practices Time Line Guide:  http://www.dnso.org/dnso/notes/20010813.GA-BP-PartIII.html