UDRP Review and Evaluation

Terms of Reference

The ICANN Board resolved at its October 24, 1999 special meeting to proceed with the implementation of a uniform dispute resolution policy (UDRP) set forth in its Resolution 99.81 using the implementation documents approved in its Resolution 99.112 (see http://www.icann.org/minutes/ minutes-24oct99.htm).

The ICANN Board further resolved that the President and General Counsel of ICANN monitor the ongoing operation of the administrative dispute–resolution mechanism described in Paragraph 4 of the UDRP and to make such adjustments to the UDRP’s implementation from time to time as they determine appropriate, including adjustments to the terms and extent of provisional approval of dispute-resolution service providers.

The DNSO Names Council has since adopted in its 2001-2002 business plan a review and evaluation of the Uniform Dispute Resolution Policy, and the establishment of an Interim Committee to propose terms of reference for an NC task force or other group to conduct such review and evaluation (see http://www.dnso.org/dnso/notes/2001-02.NCbusinessplan.html).  The interim committee consists of the following Names Council members:  Caroline Chicoine (IP), Milton Mueller (NCDNH), Oscar Alejandro Robles Garay (CCTLD), Miriam Sapiro (gTLD) and Ken Stubbs (Registrar).  The interim committee has met via e-mail and their discussions are archived at [Elisabeth – I could not find URL on website; please insert].  Based on these discussions, the Interim Committee proposes the following UDRP review and evaluation schedule:

June 15 – July 31

The interim committee shall constitute a Task Force to create a questionnaire to be distributed to the public inquiring into various aspects of the existing UDRP.  The interim committee shall solicit one individual from each of the following interest groups to be a part of this Task Force:

Business Constituency

ccTLD Constituency

gTLD Constituency

IP Constituency

ISP Constituency

NCDNH Constituency

Registrar Constituency

Complainant

CPR Panelist

CPR Provider

eResolution Panelist

eResolution Provider

NAF Panelist

NAF Provider

Respondent

WIPO Panelist

WIPO Provider

GA Member not already included in any of the above groups

The questionnaire shall be created with an eye toward identifying areas and issues that need to be addressed by a working group through a bottoms up process within the DNSO, including without limitation:

- forum shopping

- publication of complaints and answers

- appeals

- reverse domain name hijacking

- quality of decisions

- speed of decisions

- precedential affect of decisions within and outside of UDRP

- costs

- continuity of decisions among and within panels

- res judicata effect of decisions within and outside the UDRP

- requirements for bad faith (i.e., domain name registration and/or use)

While the questionnaire will be in English, to the extent feasible, the Task Force will attempt to have it translated in other languages.

August 1 – September 1

Questionnaire submitted to public for response at least via ICANN’s website, and via each UDRP provider’s website where permitted.

August 1 – October 10

Task Force reviews results of questionnaire, as well as any third party studies directed to the UDRP including without limitation the Syracuse University study, the Max Plank Institute study and the Rose Communication study.  Based on the results of the questionnaire and those studies, the Task Force shall prepare a Report summarizing issues to be addressed by one or more working groups and defining the charter for each such working group.  Again, the Task Force will attempt to translate this Report from English into as many other languages as possible.

October 11 – October 25

The Task Force’s Report shall be submitted to the Names Council for comment.

October 26 – November 1

The Task Force shall amend its Report based on the comments received by the Names Council.

November 2 – November 9

Amended Report submitted to Names Council for final review and approval.

November 12

Report is published and working groups identified in Report are created and announced at ICANN’s annual meeting in Los Angeles.

Document Name:	UDRP Terms of Reference

Author/Owner:	Chicoine, Caroline G.

Revisions Requested by:

Client #:	3999

Client Name:	Thompson Coburn

Matter #:	7000

Matter Name:	Office

PCDocs #:	1626014

Version #:	1

Typist/User Name:	Crocker, Donna

Application:	MS Word

Today's Date:	June 5, 2001

Abstract:	Typed handwritten notes

DO NOT DISCARD THIS PAGE

The Board also resolved to request the General Counsel, with the assistance of staff, to prepare a summary of matters arising in the drafting process that should be considered as possible future refinements to the UDRP and to transmit that list to the DNSO for its study of those maters, with a view toward submission to the Board for the year 2000 of any recommendations the DNSO may have for such refinements.  To date, the DNSO has not received such a summary.

Miriam Sapiro is substituting for Roger Cochetti.